## Sheet1
Outcome Premise | Outcome | Description | Complete (Y/N) | Contributor | Directory stored
Drone Body |  |  |  |  | Need to be able to prove outcome
- | CAD | Fusion 360 design for drone body | Y | Ben, Kaden | Github: Surveilia/DroneBody
- | Test Assembly PLA | Assembly and print of design using PLA 20% infill | Y | Kaden | Discord: DroneFrame
- | Component fit | Components fit on the body and tolerance met | Y | Kaden | Discord: DroneFrame
- | PETG Print 50% Infill | Successful reprint of drone with PETG at 50% infill | Y | Chase, Kaden | In Kaden's possesion
- | PETG Assembly and Fit | Retest of PETG print fit and assembly | Y | Chase, Kaden
Software
Organization | Layout | GUI is well designed and layed out neatly | Y | Chase, Ethan | Github: https://github.com/Surveilia/GroundStation
- | Data layout | Data can be read visibly in the layout: This includes Tabs for data, and graphing tools | Y | Chase, Ethan | Github: https://github.com/Surveilia/GroundStation
Data handling | Filing Protocol Design | Files will be used to store settings and data. Protocol must be design to allocate and store data in a packet contained within files. Data must be overriden as user changes configurations This task is for configurable settings, not data collection. | Y | Chase, Ethan | Github: https://github.com/Surveilia/GroundStation
- | Data distribution | Data from files is distributed to appropriate layout components. Ie, configurable data is displayed in 'settings'. Collected data is stored in 'stats' | Y | Chase, Ethan | Github: https://github.com/Surveilia/GroundStation
Communication | Comm. Protocol Design |  | Y | Chase, Ben | Github: https://github.com/Surveilia/UDP // Discord: Communication/UDP
- | Comm. Protocol Acceptance |  | N | Chase, Ethan, Ben | Github: https://github.com/Surveilia/UDP // Discord: Communication/UDP
- | UDP sends a message | UDP on Pi can contact a desktop computer | Y | Ben | Github: https://github.com/Surveilia/UDP // Discord: Communication/UDP
- | UDP sends image | UDP can send image to desktop | Y | Ben | Github: https://github.com/Surveilia/UDP // Discord: Communication/UDP
- | UDP parse | UDP message can be parsed to GUI | Y | Ben | Github: https://github.com/Surveilia/UDP // Discord: Communication/UDP
- | UDP Video | UDP can send video to desktop | Y | Ben | Github: https://github.com/Surveilia/UDP // Discord: Communication/UDP
- | UDP Video Parse | UDP video can be parsed by desktop | optional |  | Github: https://github.com/Surveilia/UDP // Discord: Communication/UDP
- | UDP File Transmission | UDP can send any file format | Y | Ben | Github: https://github.com/Surveilia/UDP // Discord: Communication/UDP
AI
Camera | Views images |  | Y | Ben | Discord: AI :: Github: https://github.com/Surveilia/GroundStation
- | Recognizes people |  | Y | Ben | Discord: AI :: Github: https://github.com/Surveilia/GroundStation
- | Recognizes people with consistency and control |  | Y | Ben | Discord: AI :: Github: https://github.com/Surveilia/GroundStation
- | Can be trained to recognize individuals |  | Optional | Ben | Discord: AI :: Github: https://github.com/Surveilia/GroundStation
- | Can recognize 2+ people in a frame |  | Y | Ben | Discord: AI :: Github: https://github.com/Surveilia/GroundStation
ArduPilot
Flight Controller | ArduPilot installed |  | Y | Chase
- | Mission Planner interfaces |  | Y | Chase | D:\School\Year3\Proofs\MissionPlanner\MissionPlannerValidation.mp4
Motors |  | Motors run in a manner consistent with PID needs
Single motor | Motor runs | - | Y | Chase, Kaden | Discored/boady prototype/flight/youtube video oct 11,2021
- | PWM on motor changes speed | - | Y | Chase, Kaden
Dual motor | Motors runs | - | Y | Chase, Kaden
- | PWM on motor changes speed | - | Y | Chase, Kaden
Quad motor | All motors run | - | Y | Chase, Kaden
- | All motors have variable speed | - | Y | Chase, Kaden
PID | Controls 2 motors on balance | PID stabalizes 2 motors on balance | N | Chase, Kaden
- | Controls all motors in flight | PID stabalizes drone in flight | N | Chase, Kaden
Pi |  | Everything to do with Pi tasks and Compute Module 4
Camera | Takes images |  | Y | Ben | Discord: AI
- | Takes videos |  | Y | Ben | Discord: AI
- | Stores videos and images |  | Y | Ben | Discord: Communication/UDP
CM4 | Voltage Regulator on PCB |  | Y |  | External Voltage Regulator
- | Schematic Complete | Schematic and rule checks finished | Y | Chase, Kaden
- | PCB Draft Complete | PCB layout (before Faculty review) complete | N | Chase, Kaden
- | PCB design complete | Faculty sign off | N | Chase, Kaden
- | PCB printed | JLCPCB print complete | N
F7 Flight Controller
Controls | Accepts Manual interrupt and control | Can be interrupted by a manual controller and controlled | Y
- | Follows Mission Planner | Follows route from mission planner | N
- | Controls drone | Has positive control of the drone | N
- | Has emergency flight cancellation interrupt | Cancels the flight and lands | N
PCB
| CM4 | CM4 Schematic | Y | Chase, Kaden | https://github.com/Surveilia/ComputeModule4
| - | CM4 Layout | N | Chase, Kaden
| Pi Zero Daughter Board | Schematic | Y | Kaden
| - | Layout | Y | Kaden
| - | Assembled and Works | N | JLCPCB
Recomendations